## Sheet1
Screen | Mandatory Test Cases (2) | Comments | "Good-to-Have" Refinement (2) | Comments
🔐 Login | 1. Auth Entrance: Log in with demo credentials. | I don’t have any credentials setup and It’s a open login where we have a Demo Login icon to click and directly get directed to Dashboard screen which is the landing Home page. | 3. Persistent Re-entry: Log out and log back in to ensure session state resets. | We don’t have any set of users created through IAM for credentials nor do we have capabilities to integrate Google Login and syncing with database
| 2. Session Threading: Verify a unique thread_id is generated for the session memory. | Lets get a login experience to access application and also becomes a trigger to capture data and enhance UX [Input: create a popup which appears before being directed to landing page where Name is captured; Output: Use name to display a greeting message and a AI generated brief of the day giving powerful insights about the day ahead | 4. Secure Header Check: Verify X-API-Key is active. | I need to create a API key specifically for this project and add them to the secure key vault on Google Cloud. Our WINNER SOLUTION for SUBMISSION should consider the AI scoring parameters around Code Quality, Security, Accessibility, Google service integration, Testing, Efficinecy and Problem Statement Alignment
🏠 Dashboard | 1. Live Stats Sync: Confirm "Live Docs" count matches AlloyDB records. | I did try injecting documents through the UI Document Vault and confirmation that event was successful and balloons flew but there were no documents found in the Bucket nor any entries were made in the database. For testing purposes I had to directly add the Documents into the Bucket via Cloud Console. The Document counter on the Dashboard does not detect the count of documents in the vault. Add Screenshots | 3. System Pulse: Verify the "Active" status indicator reflects the backend connection. | Ensure all the relevant data point names are showcased which can be viewed as live connectivity status from backend to frontend
| 2. Notification Toast: Verify real-time alerts appear when a meeting is scheduled. | The Chat Swarm was not creating any notifications. I was able to do it yesterday through the gateways but the frontend through Cloud Run is unable to render any content. We need to check its connections and ensure the app.py is designed to showcase its capability through the frontend as a live experience rather than just theoretical explanation | 4. Action Metric: Verify Task/Event counts update after a swarm action. | Did not observe
💬 Swarm Chat | 1. The RAG Proof: Ask a deep question about an ingested doc (e.g., "What are the hackathon rules?"). | Through the Cloud Run deployed frontend I could not recreate the RAG we observed yesterday while we launched the app through proxy connections. The audit shows as Success on the UI but no session IDs or any data capture is occurring in the tables. | 3. Swarm Trace Vision: Expand the "🧠 Trace" to see the sub-agent chain of thought. | I was able to see the Trace but could not verify if the trace output remains the same
| 2. Multi-Step Intent: Ask to "Schedule a sync based on the doc content." | The UI is not displaying this workflow eventhough it has this capability. | 4. Context Loop: Ask a follow-up question that relies on the previous answer. | Did not work on this Cloud Run instance
📤 Doc Vault | 1. Atomic Ingestion: Upload 1 file and verify ingestion completion. | Not working, have already inlcuded this UX observation | 3. Format Integrity: Test .txt vs .md parsing. | Both worked while directly adding into Bucket yesterday. Even on UI when I parsed both .txt and .md files I got successful completion message but the files were not showing in the bucket
| 2. Batch Sprint: Upload 3-5 files simultaneously and check the batch progress bar. | Not working, have already inlcuded this UX observation | 4. Immediate Impact: Verify the Dashboard count updates without a manual page refresh. | I did not observe
📋 Task Manager | 1. Queue Visibility: Confirm tasks created in Chat appear in the list with pending status. | I could not recreate these steps from this UI | 3. State Change: Verify status updates in the UI (if implemented). | Did not observe
| 2. Plan Expansion: Expand a task to see its multi-step "Execution Plan." | I was able to see the message and audit trail data appear | 4. Sorting Logic: Ensure newly created tasks appear at the top. | Did not observe
📅 Calendar | 1. Chronological View: View meetings in the correct time-order. | We need to include capability to display a calendar with views such as daily, weekly , monthly and yearly. Also ensure the schedule related output follows chronology of events. | 3. Document Linkage: Check if "Attached Docs" links are visible on the event card. | Did not observe
| 2. Entity Details: Verify Participants and Start/End times are accurate. | Ensure the task entry created in the calender is available to be read/edit/update. | 4. Empty State: Verify friendly UI when no meetings are scheduled. | Did not observe
🛡️ Audit Hub | 1. Trace Persistence: Locate the specific Decision ID for your most recent chat action. | I could not recreate these steps from this UI | 3. JSON Raw Inspection: View raw metadata for debugging performance. | Did not observe
| 2. Telemetry Path: Verify every agent (Orchestrator -> Sub-Agent -> Notify) is logged. | This was possible yesterday when we launched the UI directly from Streamlit via the terminal web preview through port changed to 8501 | 4. Thread Isolation: Ensure logs are mapped to the correct user thread. | Did not observe